## Slide 1: Last Week: EVIMO For Image Classification
EVIMO Data: (703, 2, 480, 640)
Using just 1 sequence
703 total bins, 5000 microseconds each
  Using 5000 because masks used to see if object in frame are generated at rate corresponding to 703 bins
Labels for Image Classification:
Assigning label of 1 if object in frame, 0 otherwise
Lenet-Decolle Model:
Increased model size to accommodate larger image sizes
  Moved code over to desktop for GPU acceleration
Modified model & parameter initialization for new data dimensions
  Previously (100, 100, 2, 28, 28)
  Now (703, 2, 480, 640)
Model not yet exceeded 53.61% accuracy (after 40 epochs)

## Slide 2: This Week
Further modified EVIMO data for input into model
  Splitting each frame into bins
  EVIMO now of format: (Frames/batch size, Bins per frame, p, x, y)
  NMNIST data of format: (T, batch size, p, x, y)
Fixed alignment of frames in dataset
  EVIMO frames are not all same length
Set up test dataset
  50% all 0’s, 50% all 1’s
Model accuracy still not improving
  Highest accuracy ~55%

## Slide 3: EVIMO For Image Classification, 10/31
EVIMO Image Classification works & trains
  Accuracy ~90% after 1 epoch for 2 label classification
Using NMNIST Data:
  Found I was using too few bins per frame for EVIMO data
    Was using 4, found 16 worked well, 100 was too many
Updated EVIMO data storage process
  Significantly sped up data load time, allowing faster training
  ~12 min epoch
Previously:
Now:

## Slide 4: EVIMO for Object Detection 11/7
Should be able to get both bounding boxes and class from one model
  Single Shot MultiBox Detectors able to model object detection as regression/classification program
Preliminary tests of using bounding box as target:
  Model unable to adjust quickly enough for the large values of x, y
    During training, saw variations of up to 5 in readouts, when target bounding boxes have x, y of 300
    Tried with several learning rates
    May try adding Softmax loss
Updated model accuracy / error to be based on IoU

## Slide 5: EVIMO for Object Detection 11/14
Updated event representation to Voxel Grid
Created SSD Heads for object detection model
  Using same LIFLayer Conv2D from Lenet-Decolle Model
Working on using current Lenet-Decolle model as backbone for SSD Heads
Implementation of loss function for object detection model?

## Slide 6: Alternate Object Representations 11/28
Current method:
  Use bounding boxes (x, y, h, w)
  Anchor boxes in model used to get final bounding box
Keypoint Triplets (CenterNet):
  Use corners to determine object
  Center point determines class
  No anchor boxes
Cascade R-CNN:
  Use bounding boxes
  No anchor boxes
  Model has sequence of detectors with increasing IoU thresholds to filter to best bounding boxes

## Slide 7: Potential Models for Obj Det 12/5
CenterNet (Keypoint Triplets):
  Use corners to determine object
  Center point determines class
  No anchor boxes
  Can predict multiple boxes
  Paper used images
Encoder-Decoder DECOLLE:
  Using bounding boxes
  Only predicts one bounding box
  Paper used events from rate-coded images